## Feuil1
Step | Task | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13
Setup | Specifications
Gantt diagram
Host Moodle server
Host Gitlab server
State of the art
Choose technologies
Explore GitLab API
Explore Moodle API
Determine feasible features
Design system architecture
Initialize project
Kanban board
Implementation | POC simple feature
GitLab API client
Module creation
Students group selection
Teachers dashboard
Students module view
Grade review
Webhooks
GitLab workflow
Evaluation | Test
User validation
Report | Final report
Midterm report
|  | halftime | [12 empty] | intermediary report |  |  |  | fulltime |  |  |  | final report
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ajouter détail pour implémentation (après)